## Contingency Evaluation
ATTACHMENT 14: Contingency Planning Tool
Site Remediation Contingency Evaluation Form
Site Name:
Project Name:
|  | Contingency Statement |  |  | Probability | Impact | Exposure | Schedule
# |  | Condition | Consequence | Status | (%) | ($) | ($) | Impact | Mitigation | Measurements | Contingency | Triggers | Assignee
Unique ID | Uncertainty/Contingency Category 1 | Capture the "likely cause" of the contingency. Be detailed enough so that you can start forming mitigation plans. | Capture the result of the contingency, should it happen. If the consequences cannot be mitigated, you will have to deal with them in a contingency plan. | Active, retired, no concern | Estimate of the probability the contingency will occur. | Estimate of the amount of impact or severity of the contingency. | Probability x impact in $. Sort by this column to prioritize biggest $ impacts. | Estimate of the amount of time delay/extension that could be caused by the contingency | Document plans to lower the probability or to lower the impact ahead of time. It may require a more detailed plan written up separately. | Describe what measurements and at what frequency they will be taken to monitor for the occurrence of the contingency | Identify what would have to be done if the contingency were to become reality. This may require a more detailed plan documented separately. | Identify what would prompt you to execute the contingency plan. | Identify who is responsible for tracking this contingency and its changes in probability and impact. The assignee is not necessarily the person responsible for solving the problem, as contingencies often require escalation outside the team.
High Priority
Moderate Priority
Notes:
1. Consider Uncertainty/Contingency Categories of Performance, Schedule, PM Experience, Client, Scope, Resources, Budget, Technology, Endorsement, and Contract.
Note on E11: Use this column to note the status of items that are still active, have passed or are no longer of concern.
Note on F11: Probability of occurrence (% chance)
Note on G11: Potential impact in $. (Best assessment of overall impact)

## Schedule Impacts
Site Remediation Schedule Impact Assessment
Site Name:
Project Name:
Site | Milestone | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065 | 2066 | Comments
■ | Baseline schedule expectation
■ | Schedule deviation should a couple high probability contingencies occur
■ | Schedule deviation should all high probability contingencies occur

## Cost Impacts
Site Remediation Life Cycle Cost Contingency Impact Estimate
Site Name:
Project Name:
Procedure: Input the projected project costs (Current Estimated Annual Cost) by year for the site as specified in the existing administrative records. Using the Contingency Evaluation sheet, input the applicable contingency number(s) and best/worst case contingency cost estimates. The spreadsheet will use the current budget and contingency to calculate a best and worst case annual cost and estimate to complete.
Current Est.
Year | Annual Cost | Cost Element Description | Contingency | Contingency Condition Description | Contingency Cost |  | Estimate to Complete (ETC) |  | Notes
|  |  | ID |  | Best Case | Worst Case | Best Case | Worst Case
2009 | [6 empty] | 0 | 0
2010 | [6 empty] | 0 | 0
2011 | [6 empty] | 0 | 0
2012 | [6 empty] | 0 | 0
2013 | [6 empty] | 0 | 0
2014 | [6 empty] | 0 | 0
2015 | [6 empty] | 0 | 0
2016 | [6 empty] | 0 | 0
2017 | [6 empty] | 0 | 0
2018 | [6 empty] | 0 | 0
2019 | [6 empty] | 0 | 0
2020 | [6 empty] | 0 | 0
2021 | [6 empty] | 0 | 0
2022 | [6 empty] | 0 | 0
2023 | [6 empty] | 0 | 0
2024 | [6 empty] | 0 | 0
2025 | [6 empty] | 0 | 0
2026 | [6 empty] | 0 | 0
2027 | [6 empty] | 0 | 0
2028 | [6 empty] | 0 | 0
2029 | [6 empty] | 0 | 0
2030 | [6 empty] | 0 | 0
2031 | [6 empty] | 0 | 0
2032 | [6 empty] | 0 | 0
2033 | [6 empty] | 0 | 0
2034 | [6 empty] | 0 | 0
2035 | [6 empty] | 0 | 0
2036 | [6 empty] | 0 | 0
2037 | [6 empty] | 0 | 0
2038 | [6 empty] | 0 | 0
2039 | [6 empty] | 0 | 0
2040 | [6 empty] | 0 | 0
2041 | [6 empty] | 0 | 0
2042 | [6 empty] | 0 | 0
2043 | [6 empty] | 0 | 0
2044 | [6 empty] | 0 | 0
2045 | [6 empty] | 0 | 0
2046 | [6 empty] | 0 | 0
2047 | [6 empty] | 0 | 0
2048 | [6 empty] | 0 | 0
2049 | [6 empty] | 0 | 0
2050 | [6 empty] | 0 | 0
2051 | [6 empty] | 0 | 0
| 0 | Total Projected Estimate-to-complete (w/out contingency) |  |  |  |  | 0 | 0

## Menu Lists (hidden)
0 - Not Applicable | 0
1 - <30% Complete | 1
2 - 30-60% Complete | 2
3 - 60-90% Complete | 3
4 - >90% Complete | 4
0 - Not Applicable | 0
1 - <30% Certain | 1
2 - 30-60% Certain | 2
3 - 60-90% Certain | 3
4 - >90% Certain | 4